Amahle Magocoba

ST10351403

PROG6212

CMCS Project Plan

## Project Plan

### Phase 1: Development of the Prototype (Weeks 1-5)

- Database schema design, UML, and requirement analysis.

- Create the Manager, Coordinator, and Lecturer GUI wireframes.

- Use role-based navigation in conjunction with MVC architecture.

- Include fictitious Claim and Login/Register pages.

- GitHub commits provide version control.

- Part 1 Report (references, project plans, GUI, and UML).

### Phase 2: Database Integration & Business Logic (Weeks 6-10)

| Task | Dependencies | Timeline |
| --- | --- | --- |
| Set up Entity Framework Core | Completed prototype | Week 6 |
| Implement Database Migrations (SQL) | EF Core setup | Week 7 |
| Connect Models to Database | Database migrations | Week 7-8 |
| Implement CRUD for Claims | Model–DB integration | Week 8 |
| File Uploads (Documents) | CRUD working | Week 9 |
| Testing Database Operations | CRUD and uploads | Week 10 |

### Phase 3: Authentication & Role Management (Weeks 11-13)

| Task | Dependencies | Timeline |
| --- | --- | --- |
| Implement ASP.NET Identity | Database ready | Week 11 |
| Role-Based Access (Lecturer, PC, Manager) | Identity implemented | Week 11-12 |
| Secure Navigation (show/hide links by role) | Role-based access | Week 12 |
| Testing Authentication Flows | All roles implemented | Week 13 |

### Phase 4: Advance Features and Reporting (weeks 14-16)

| Task | Dependencies | Timeline |
| --- | --- | --- |
| Generate Reports for Managers | CRUD + roles in place | Week 14 |
| Export to PDF/Excel | Report generation | Week 14-15 |
| Improve UI (Bootstrap, AJAX updates) | Role-based dashboards ready | Week 15 |
| Testing (Usability + Performance) | All features complete | Week 16 |

### Phase 5: Final Intergration and Documentation (weeks 17-18)

| Task | Dependencies | Timeline |
| --- | --- | --- |
| Final System Testing | All modules | Week 17 |
| Bug Fixes & Optimization | Testing feedback | Week 17 |
| Final Report Writing | Prototype + DB + Auth done | Week 18 |
| Submission Preparation (Docs + GitHub) | Report finalized | Week 18 |

The CMCS project is structured into five phases:

- Prototype development (Weeks 1–5): includes requirement analysis, UML design, GUI wireframes, and an ASP.NET Core MVC prototype with role dashboards, login/register, and claims pages.

- Database Integration (Weeks 6-10): Set up Entity Framework Core, create the database schema, enable CRUD for claims, and allow document uploads.

- Authentication and Roles (Weeks 11-13): Implement ASP.NET Identity for login security, enforce role-based access (Lecturer, Coordinator, Manager), and ensure secure navigation.

- Advanced Features (Weeks 14-16): Enable report production and export to PDF/Excel, improve the UI with Bootstrap and AJAX, and perform usability testing.

- Final Integration and Documentation (weeks 17-18): Complete system testing, problem corrections, final report authoring, and submission preparation using GitHub evidence.